## Sheet1
1 | For reference only | 23 | For reference only | For reference only | For reference only | 2 | 25 | For reference only | 24 | For reference only | 26 | 4 |  | For reference only | For reference only |  | For reference only |  | 27 | For reference only | 28 | For reference only | 44 | 46 | 49 | 63
2020-04-13
Location
Row # | Person Responsible | Utility Unique ID #1 | TO Tracker AA Status | TO Tracker BC Status | Order | Project Name | Utility Unique ID #3 | MAT | Utility Unique ID #2 | T.Dot Project Name | Change in Unique ID | City | County/Counties | AA EDRS No. | Project Kickoff | A | Business Case Date | A | Year of Advanced Authorization | AA Collected (Yes/No/N/A) | Year of Business Case Approval | BC Collected (Yes/No/N/A) | Project Status | Construction Start Date | Current Projected or Actual In-Service Date | Notes
148 | Levya, Jesus | 5756012 | Collected | N/A | 74000622 | BELLOTA - WARNERVILLE RECONDUCTOR | 60 | 60X | T.0000043 | Bellota-Warnerville 230kV Reconductor | TBD | N/A | 039-San Joaquin County | 2014-22317 | 2016-03-23 | A | 2022-02-01 |  | 2014 | YES | N/A | N/A | Permitting | 2022-05-02 | 2023-05-01
149 | Levya, Jesus | 5766750 | Collected | N/A | 74001792 | RED BLUFF-COLEMAN REINFORCEMENT | 60 | 60X | T.0000013 | Coleman - Red Bluff Project | 5738259 | N/A | 045-Shasta County | 2011-52142 | 2018-05-01 | A | 2021-08-06 |  | 2011 | YES | N/A | N/A | Permitting | 2022-07-29 | 2024-02-15
151 | Levya, Jesus | 5785878 | Collected | N/A | 74026743 | RECONDUCTOR BELLOTA-COTTLE 230 KV | 60 | 60X | T.0000043 | Bellota-Warnerville 230kV Reconductor | TBD | N/A | 005-Calaveras County |  | 2016-03-23 | A | 2022-02-01 |  | 2014 | YES | N/A | N/A | Engineering more than 50% complete | 2023-11-01 | 2025-05-30
245 | Levya, Jesus | 5766696 | Collected | N/A | 74001791 | NV_ INSTALL (2) CAPACITOR BANKS PLAINFIE | 61 | 61X | T.0000007 | Vaca - Davis Voltage Conversion Project | 5738814 | Vacaville | 048-Solano County | 2012-08941 | 2018-10-25 | A | 2029-04-25 |  | 2012 | YES | N/A | N/A | Engineering less than 50% complete | 2029-08-02 | 2029-12-19
531 | Levya, Jesus | 5776770 | Collected | N/A | 74014815 | Tesla 230kV MPAC | 67 | 67A | T.0003456 | Tesla 115kV MPAC | TBD | Tracy | 001-Alameda County | 2016-53181 | 2023-01-27 |  | 2025-02-11 |  | 2018 | YES | N/A | N/A | Planning | 2026-03-13 | 2028-09-28
609 | Levya, Jesus | 5777912 | Collected | N/A | 74015513 | 74015513_PITTSBURG - SAN MATEO TWR REPL | 70 | 70S | T.0003592 | Pittsburg - San Mateo 230kV Twr Repl | TBD | N/A | 001-Alameda County |  | 2018-03-26 | A | 2020-09-21 |  | 2017 | YES | N/A | N/A | Permitting | 2022-01-11 | 2023-01-05
611 | Levya, Jesus | 5777910 | Collected | N/A | 74015511 | 74015511_NEWARK - AMES 115KV TWR REPL | 70 | 70S | T.0003590 | Newark - Ames 115kV Twr Repl | TBD | N/A | 001-Alameda County |  | 2018-03-28 | A | 2020-12-01 |  | 2017 | YES | N/A | N/A | Permitting | 2022-02-24 | 2023-02-10
612 | Levya, Jesus | 5777913 |  |  | 74015514 | 74015514_W SAC - BRIGHTON 115KV TWR REPL | 70 | 70S | T.0003593 | W SAC - BRIGHTON 115KV TWR REPL | TBD |  | 041-San Mateo County |  | 2018-04-09 | A | 2020-12-22 |  |  |  | N/A | N/A | Permitting | 2022-05-13 | 2023-03-21
613 | Levya, Jesus | 5777901 |  |  | 74015501 | 74015501_IGNACIO - ALTO - SAUSALITO 60KV | 70 | 70S | T.0003580 | Ignacio - Alto - Sausalito 60kV | TBD |  | 021-Marin County | 2017-111244 | 2018-03-14 | A | 2022-02-08 |  | 2017 |  | N/A | N/A | Permitting | 2022-08-30 | 2023-07-20
662 | Levya, Jesus | 5508619 | Uncollected | Uncollected | 31440171 | TRANSMISSION POLE RESTOCKING ORDER | 70 | 70Y | N/A |  | TBD |  | 039-San Joaquin County | [9 empty] | Engineering more than 50% complete | OAI | 2021-05-13
663 | Levya, Jesus | 5508619 | Uncollected | Uncollected | 31427618 | TRANSM VALMONT MEXICO PLNT 300 PLE ORDER | 70 | 70Y | N/A |  | TBD |  | 039-San Joaquin County | [9 empty] | Engineering more than 50% complete | OAI | 2021-03-04
664 | Levya, Jesus | 5508619 | Uncollected | Uncollected | 31456632 | TLINE WSIP 100 POLE ORDER | 70 | 70Y | N/A |  | TBD |  | 039-San Joaquin County | [9 empty] | Engineering more than 50% complete | OAI | 2021-07-01
665 | Levya, Jesus | 5508619 | Uncollected | Uncollected | 31455652 | TAPP POLE ORDER | 70 | 70Y | N/A |  | TBD |  | 039-San Joaquin County | [9 empty] | Engineering more than 50% complete | OAI | 2021-06-27
666 | Levya, Jesus | 5508619 | Uncollected | Uncollected | 31454735 | TRANSM VALMONT-MEXICO PLNT 900POLE ORDER | 70 | 70Y | N/A |  | TBD |  | 039-San Joaquin County | [9 empty] | Engineering more than 50% complete | OAI | 2021-06-14
667 | Levya, Jesus | 5508619 | Uncollected | Uncollected | 31425890 | TRANSMISSION VALMONT 900 POLE ORDER | 70 | 70Y | N/A |  | TBD |  | 039-San Joaquin County | [9 empty] | Engineering more than 50% complete | OAI | 2021-02-12
668 | Levya, Jesus | 5508619 | Uncollected | Uncollected | 31455492 | TRINITY MEYERS POLE ORDER | 70 | 70Y | N/A |  | TBD |  | 039-San Joaquin County | [9 empty] | Engineering more than 50% complete | OAI | 2021-06-25
669 | Levya, Jesus | 5508619 | Uncollected | Uncollected | 31455626 | SABRE 500 POLE ORDER | 70 | 70Y | N/A |  | TBD |  | 039-San Joaquin County | [9 empty] | Engineering more than 50% complete | OAI | 2021-06-26
731 | Levya, Jesus | 5766463 |  |  | 74000344 | CHSR INTERCONNECTIONS T-LINE SITES 4-7 | 82 | 82B | T.0000005 | CHSR Interconnections, Sites 4-7 | TBD |  | 020-Madera County | 2016-111089 | 2016-12-14 | A | 2031-08-22 |  | 2016 |  | N/A | N/A | Planning | 2032-05-12 | 2034-08-01
732 | Levya, Jesus | 5766318 |  |  | 74000340 | CHSR INTERCONNECTIONS T-LINE SITES 8-13 | 82 | 82B | T.0000006 | CHSR Interconnections, Sites 8-13 | TBD |  | 020-Madera County | 2015-108611 | 2016-02-23 | A | 2031-11-18 |  | 2015 |  | N/A | N/A | Planning | 2033-03-14 | 2035-01-26
763 | Levya, Jesus | 5766464 |  |  | 74000345 | CHSR INTERCONNECTIONS SUB SITES 4-7 | 82 | 82W | T.0000005 | CHSR Interconnections, Sites 4-7 | TBD |  | 020-Madera County | 2016-111089 | 2016-12-14 | A | 2027-05-28 |  | 2016 |  | N/A | N/A | Planning | 2028-02-17 | 2030-01-01
764 | Levya, Jesus | 5766319 |  |  | 74000341 | CHSR INTERCONNECTIONS SUB SITES 8-13 | 82 | 82W | T.0000006 | CHSR Interconnections, Sites 8-13 | TBD |  | 020-Madera County | 2015-108611 | 2015-11-09 | A | 2032-02-11 |  | 2015 |  | N/A | N/A | Planning | 2032-11-01 | 2027-01-01
766 | Levya, Jesus | 5766383 |  |  | 74000343 | CALTRAIN INTERCONNECTIONS SUB SITE 1 | 82 | 82W | T.0000004 | Caltrain Interconnections Site 1 | 5743532 |  | 041-San Mateo County | 2015-108624 | 2016-05-12 | A | 2018-12-11 | A | 2015 |  | 2017 |  | Construction | 2019-05-08 | 2021-04-30
1080 | Levya, Jesus | 5747900 |  |  | 74000580 | DRUM-RIO OSO #1-115KV IMPRV (STEEL) | 94 | 94A | T.0000036 | Drum-Rio Oso #1 115kV Reliability | TBD |  | 029-Nevada County | 2012-18510 | 2017-12-29 | A | 2022-01-04 |  | 2012 |  | N/A | N/A | Planning | 2021-05-03 | 2022-02-24
1081 | Levya, Jesus | 5784525 |  |  | 74024880 | Drum-Rio Oso #2 Reliability | 94 | 94A | T.0000036 | Drum-Rio Oso #1 115kV Reliability | TBD |  | 029-Nevada County |  | 2019-03-07 | A | 2022-01-04 |  |  |  | N/A | N/A | Engineering less than 50% complete | 2022-05-03 | 2023-02-27
1165 | Levya, Jesus | 5777333 |  |  | 74014843 | BUTTE: REPL BK 2 AND UPGRADE EQUIPMENT | 94 | 94D | T.0003457 | Butte 115kV Sec MA BAAH DBSB | TBD |  | 004-Butte County |  | 2023-02-27 |  | 2024-03-08 |  |  |  | N/A | N/A | Planning | 2024-11-15 | 2026-09-24